## Tabelle1
Risk | Group | Probability | Loss | Combined Risk (Prob x Loss) | Rank | Mitigation
Project Planning schedule was not realistic | Schedule Risk | High | Medium | High | 1 | Check project status regularly and see if it is on track. Adapt project plan if not on track anymore
Team Members are not experienced enough and can not learn needed skills fast enough | Performance Risk | Medium | Severe | High | 2 | Split tasks so every team member has to only learn his field
Needed Materials are not delivered in time | Schedule Risk | Low | Severe | High | 3 | Whole project plan would need to be moved back in time
Project Requirements can not be met in the scheduled time | Performance Risk | Medium | Medium | Medium | 4 | Reserve enough time to work on project by all project members
Technology not available (we can not find suitable effect algorithms) | Performance Risk | Low | Severe | Medium | 5 | Preparation before project start to check for technology availability
Raspberry Pi Processor not powerful enough | Performance Risk | Medium | Severe | Medium | 6 | Prepare to use different algorithms that need less resources
Changes to specification occur | Schedule Risk | High | Low | Medium | 7 | Group has to be able to adapt
Forgot Tasks or Work packages in project Planning | Schedule Risk | Medium | Medium | Medium | 8 | Review project plan when work starts regularly
There is no customer for our product | Market Risks | Low | Critical | Medium | 9 | Minimizing the loss of the killed project
Audio Input/Output is not compatible to other modules | Performance Risk | Low | Severe | Medium | 10 | Stick to specification
Power source on rack is not compatible to Raspberry Pi | Performance Risk | Low | Severe | Medium | 11 | Provided cables can be adapted with a little soldering
Raspberry Pi Chip cost increases | Cost Risk | Low | Severe | Medium | 12 | Be prepared to use other components for sourcing
Group member gets sick | Risks associated with external hazards | Medium | Low | Low | 13 | Other group members have to compensate, plan for buffer time at the end
Setup of Linux base system does not work on Raspberry | Performance Risk | Low | Low | Low | 14 | Aquire linux expertise
Missunderstandings in project goal | Performance Risk | Low | Medium | Low | 15 | Try to review project at half of implementation (ask questions after lecture to make sure requiremnts are understood)
Team Members do not harmonize well | Governance Risk | Low | Medium | Low | 16 | Keep up the group spirit from the start
Not all parts are delivered as expected | Operational Risks | Low | Medium | Low | 17 | Take care when creating BOM, adapt to delivered parts

## .
Schedule Risk
Cost Risk
Performance Risk
Market Risks
Risks associated with external hazards
Legal Risks
Operational Risks
Governance Risk