## Work Packages
Work Package | Sub-WP | WP Leader | Sub-WP Leader
Project Planning |  | Daniel
| Syntesizer Research |  | All
| Course Assignments |  | Daniel
| Tracking of Project Status |  | Daniel
| Milestone Tracking |  | Daniel
Hardware |  | Samaneh
| Hardware Design |  | Samaneh & Samawat
| Sourcing of Raspberry and other Hardware |  | Daniel
| Hardware Setup (ADC & DAC) |  | Samawat
| Eurorack Housing |  | Samaneh
Sofware |  | Aleksei
| Setting up Linux OS |  | Zhi Wang
| Audio In/Output |  | Aleksei
| Feature 1: Audio Stream Record and Playback |  | Aleksei
| Feature 2: Pitch Change |  | Zhi Wang
| Feature 3: |  | Aleksei
Validation |  | Zhi Wang
| Hardware Validation |  | Samaneh
| Software Validation |  | Samawat
Documentation |  | Samawat
| Gathering Documentation |  | Samawat
| Final Report |  | Samawat

## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | MySynth - Effects Module
Enter Company Name in cell B2. Enter the Project Start date in cell E2 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell C2. | MySynth | Project Start Date: |  | 2019-01-09
Enter the name of the Project Lead in cell B3. A Scrolling Increment is in cell E3. Scrollbar is in cells H3 through M3. Increasing the scrolling increment or using the scrollbar will increment the Gantt chart timeline. An input of 0 in cell E3 resets the charting to the start of the project. | Daniel Thomer | Scrolling Increment: |  | 23
To modify the default Milestone Marker type, enter a 0, 1, or 2, in cell E5. The corresponding marker will appear in cell F5. To change the markers, modify the conditional format for that cell and the table below. Months for the dates in row 5 are displayed starting in cells H4 through cell BK4. Do not modify these cells. They are auto updated based on the project start date and scrollbar increment. Scrolling Increment: label is in cell C4. |  | Milestone Marker: |  | 2 | 2 |  | February | [27 empty] | March
Cells H5 through BK5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Dates leading up to Today are shaded. | time axis 2019-02-01 to 2019-03-28
This row contains headers for the project schedule that follows below them. Navigate from B7 through BK7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell H7 and continues through cell BK7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. Formulas in these cells help create the look of the Gantt Chart. Do not modify these cells. | Milestone Description | Assigned To | Progress | Start | No. Days | Estimated Effort (hours) | time axis 2019-02-01 to 2019-03-28
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B8 through cell F8. Sample data is in cells B8 through G32. Enter Milestone Description, assign someone to the item, enter the progress of the task as a percent of completion, enter a start date and duration of task in number of days. The Gantt chart will auto update as the data is entered. The next instruction is in cell A33. | Project Planning
| Syntesizer Research | All | 100% | 2019-01-09 | 14 | 50
| Course Assignments | Daniel | 25% | 2019-01-09 | 100 | 40
| Tracking of Project Status | Daniel | 10% | 2019-01-09 | 100 | 20
| Milestone Tracking | Daniel | 0% | 2019-02-28 | 5 | 20
Hardware
| Hardware Design | Samaneh & Samawat | 50% | 2019-02-01 | 21 | 20
| Sourcing of Raspberry and other Hardware | Daniel | 25% | 2019-02-18 | 13 | 10
| Hardware Setup (ADC & DAC) | Samawat | 15% | 2019-03-01 | 21 | 40
| Eurorack Housing | Samaneh | 0% | 2019-04-08 | 7 | 30
Sofware
| Setting up Linux OS | Zhi Wang | 25% | 2019-02-01 | 14 | 50
| Audio In/Output | Aleksei | 0% | 2019-02-10 | 21 | 30
| Feature 1: Audio Stream Record and Playback | Aleksei | 0% | 2019-03-01 | 28 | 40
| Feature 2: Pitch Change | Zhi Wang | 0% | 2019-03-07 | 28 | 50
| Feature 3: | Aleksei | 0% | 2019-03-14 | 14 | 25
Validation
| Hardware Validation | Samaneh | 0% | 2019-03-16 | 21 | 50
| Software Validation | Samawat | 0% | 2019-03-31 | 21 | 50
Documentation
| Gathering Documentation | Samawat | 10% | 2019-02-06 | 50 | 15
| Final Report | Samawat | 0% | 2019-04-01 | 14 | 35
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one
525
105

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, Progress as a percent of completion of the task, a Start Date and Number of days to complete the task. The Gantt chart auto updates. A scroll bar allows you to scroll through the timeline. Insert new tasks by inserting new rows. Customize the look of the chart by modifying the conditional formats. Dates up to the current day are shaded in the timeline.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.